Executive Summary:  The Sunset Tour

Overview

This document will outline the plan for hosting The Sunset Tour in six different cities. It is a 5k Run followed by and after party with a DJ, live music, and food and beverages. Most of the proceeds will be donated to the charity of your choosing: The Breast Cancer Association, Red Cross, and Make A Wish.

Business Need/Problem/Solution:

- There has yet to be a 5k run that allows people to donate to a charity of their choosing followed by entertainment.

  - People also have not been able to just sign up for certain parts of the run or after party.

- Proposed solution:

  - Host the Sunset Tour in six different cities where participants can choose one of three charities to donate their money to.

  - Allow participants three buying options; run only, both run and after party, and just the after party.

  - We will allow participants at the after party to donate money as well at each of our vendor stations

Consistency/Fit with Organization’s Mission:

Our mission is to be able to raise money for multiple charities in a 5k race that is put on in 6 different and popular locations all across the U.S. We would like the event to become an annual event in which participants will donate to The Breast Cancer Association, Red Cross, and Make A Wish Foundation. After the event we will be having a DJ for all ages and provide food from Chipotle, Buffalo Wild Wings, Coca-Cola, and MillersCoors. We will also have a band that will perform at the after party which will take place from 7-9pm.

Project Objectives

- Choose vendors to supply food and drinks for the events- 11/20/14

- Book vendors for the day of the races- Starting 11/22/14

- Connect with sponsors- 12/03/14

- Choose charities to partner with– 12/04/14

- Determine tour cities- Starting 12/17/14

- Book sites for the event in each city- Starting 12/20/14

- Create and execute the marketing campaign- Starting 1/27/15

- Construct the website for participants to register and donate- 2/04/15

- Design the courses and corresponding details for each location- Starting 2/13/15

- Secure Volunteers for each location- 2/19/15

- Receive RSVPs to determine number of participants- Starting 4/15/15

- Book entertainment for each location-5/21/15

- Rent necessary supplies and services for the event- Starting 6/11/15

Budget estimate: 1.2 million for 6 5ks