Scope Statement

Date: February 8, 20xx

Project Name: ChefCon 20xx

Project Sponsors: ??

Original Project Managers: Sammy Holquist, Anna Kaiper, and Meg Sisk

A. Business Need/Problem:

- A convention like ChefCon does not exist yet.

Vision: ??

Mission: ??

B. Project Objectives:

- ChefCon 20xx is the inaugural convention for ChefCon International, an organization that will put on an annual chef’s convention that partners with multiple sponsors to inspire people to be more active in the preparation of their food and spark greater interests in culinary arts.

- To connect and create a community of chefs ranging from amateur to professionals and food lovers in a luxurious yet leisurely setting.

  - Get smaller organizations/companies more exposure

  - Get amateur chefs more experience

  - Better informed business professionals.

  - Teach on future and sustainable cooking practices

  - Inform people on food diversity

- We expect this convention to attract a large, diverse crowd.

- There will be sectors specific to experienced chefs, novice chefs, children, vendors, etc.

- Within the convention there will be multiple sectors pertaining to different culinary techniques and markets.

Project Objectives

  - Call and schedule rooms at a convention center

  - Contact and secure sponsors and partnerships

  - Hire and train event staff on event activities

  - Secure all printed fliers, maps and banners

  - Advertise event

## C.            Project Results:

- Complete ChefCon 20xx, a chef convention

- Attract 250,000 patrons to the event

- After the convention, the revenue breaks even with the initial budget

- positive feedback from celebrity chefs

- Based upon the four previous project results, make ChefCon an annual event

## D.            Project Content:

In scope:

- Arrange location for ChefCon

- Advertisement for ChefCon

- Securing 1 Celebrity Chef speakers/demonstrators per day for keynote speaker

- Securing 3 non-celebrity industry professional speakers/ demonstrators on keynote speaker stage per day

- Securing industry professionals for events at various sectors

- Selling tickets for ChefCon

- Supplying common restaurant kitchen set-ups for all sectors except the vendors.

- Basic seating and table accommodations for guests

- Accommodations for the heads of partnership organizations for the duration of the convention (i.e. transportation services, hotels/housing, meals)

- Accommodations for the project managers for the duration of the convention (i.e. transportation services, hotels/housing, meals)

- We will pay for invited celebrity chef accommodations for the duration of the convention (i.e. transportation services, hotels/housing, meals)

- Prizes as needed

- Facilitating post event evaluation

Out of scope:

- Transportation for patrons beyond supplied shuttle services

- Hotel stay for the duration of ChefCon for patrons

- Food for vendors

- Training for convention center staff

- Training for any staff on anything that will not be directly used at ChefCon

- Hiring and training any staff for sponsors or contracted company on industry or craftsman specifics

- Prizes