## Source of Project Cost
Source of Project Cost
| PROJECT TASKS | LABOR HOURS | LABOR COST ($) | MATERIAL COST ($) | TRAVEL COST ($) | OTHER COST ($) | TOTAL PER TASK | WEEK
PROJECT INITIATION | Develop Charter | 4 | 180 | 5 | 0 | 0 | 185 | 1 | 2227.5
| Develop Scope Statement | 12 | 540 | 10 | 0 | 0 | 550 | 1
| Develop Schedule | 12 | 540 | 3 | 0 | 0 | 543 | 2 | 2590
| Develop initial Budget | 8 | 360 | 1 | 0 | 0 | 361 | 2
| Develop Communications Plan | 1 | 30 | 0.5 | 0 | 0 | 30.5 | 2
| Develop Risk Plan | 4 | 160 | 3 | 0 | 0 | 163 | 2
| Hold Kickoff Meeting | 1 | 150 | 15 | 1000 | 0 | 1165 | 4
| Subtotal | 42 | 1960 | 37.5 | 1000 | 0 | 2997.5
PROJECT PLANNING | Develop WBS | 30 | 1350 | 0 | 0 | 0 | 1350 | 3 | 4252.5
| Plan Procurement | 20 | 900 | 0 | 0 | 0 | 900 | 3
| Create other mgmt plans | 10 | 450 | 0 | 0 | 0 | 450 | 3
| Development Acceptance Test Package | 2 | 60 | 0 | 0 | 0 | 60 | 3
| Subtotal | 62 | 2760 | 0 | 0 | 0 | 2760
PROJECT EXECUTION & CONTROL | JAR Session | 12 | 5760 | 200 | 3000 | 400 | 9360 | 4 | 39887.5
| Develop Functional Specifications | 24 | 720 | 0 | 0 | 50 | 770 | 4
| Develop Preliminary Design Specification | 40 | 4800 | 0 | 0 | 50 | 4850 | 4
| Develop Detailed Design Specification | 120 | 14400 | 0 | 0 | 50 | 14450 | 4
| Develop Acceptance Test Plan | 10 | 600 | 0 | 0 | 0 | 600 | 4
| Develop Components | 120 | 7200 | 0 | 0 | 0 | 7200 | 4
| Procure Hardware | 40 | 1200 | 2000000 | 0 | 3000 | 2004200 | 5 TO 6 | 1264138.5
| Image Hardware | 400 | 24000 | 3000 | 0 | 200 | 27200 | 6 | 769954
| Perform Unit/Integration/System Test | 20 | 1200 | 0 | 0 | 0 | 1200 | 6
| Remove Old CRTs | 64 | 7680 | 500 | 0 | 6000 | 14180 | 9 | 30652.5
| Install New CRTs | 64 | 7680 | 500 | 0 | 500 | 8680 | 9
| Perform Acceptance Test | 4 | 480 | 0 | 0 | 0 | 480 | 9
| Perform Post Project Review | 3 | 720 | 0 | 0 | 0 | 720 | 9
| Provide Warranty Support | 40 | 9600 | 300 | 0 | 300 | 10200 | 9 TO 10
| Archive Materials | 2 | 90 | 0 | 0 | 50 | 140 | 10 | 10042.5
| Subtotal | 963 | 86130 | 2004500 | 3000 | 10600 | 2104230
PROJECT MANAGEMENT | Customer Progress Meetings/Reports | 20 | 7200 | 0 | 0 | 200 | 7400 | ALL
| Internal Status Meetings/Reports | 20 | 900 | 0 | 0 | 20 | 920 | ALL
| Third-Party Vendor Interface | 5 | 200 | 0 | 0 | 0 | 200 | ALL
| Interface to Other Internal Departments | 5 | 150 | 0 | 0 | 0 | 150 | ALL
| Configuration Management | 5 | 225 | 0 | 0 | 0 | 225 | ALL
| Quality Assurance | 14 | 630 | 0 | 0 | 0 | 630 | ALL
| Overall Project Management | 120 | 5400 | 0 | 0 | 0 | 5400 | ALL
| Subtotal | 189 | 14705 | 0 | 0 | 220 | 14925 |  | 1492.5
PROJECT CLOSE | Turn-over to Support | 8 | 1200 | 0 | 0 | 50 | 1250 | 10
| Hold Lessons Learned Meeting | 2 | 1540 | 0 | 300 | 160 | 2000 | 10
| Archive project materials | 1 | 45 | 15 | 0 | 0 | 60 | 10
| Subtotal | 11 | 2785 | 15 | 300 | 210 | 3310
Subtotals |  | 1267 | 108340 | 2004552.5 | 4300 | 11030 | 2128222.5
Risk (Contingency) |  | 0.15 | 16251 | 300682.875 | 645 | 1654.5 | 319233.375
Total (Scheduled) |  | 1267.15 | 124591 | 2305235.375 | 4945 | 12684.5 | 2447455.875

## Expenditures Over Time
Expenditures Over Time
|  | ITEM | COST | DATE | REASON FOR EXPENDITURE
| INSTALLATION | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| PLANNING (RFP) | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| PLANNING 2 | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| CONSTRUCTION | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| TEST & DELIVERY | Install System | 0
|  | Train Customers | 0
|  | Perform Acceptance Test | 0
|  | Perform Post Project Review | 0
|  | Provide Warranty Support | 0
|  | Achieve Materials | 0
|  | Subtotal | 0
| PROJECT TOTAL |  | 0

## Cumulative Project Costs
Projected vs. Actual Costs
MONTHLY COST
CUMULATIVE COST

## Data Worksheet
Project Data Worksheet
| WEEK | PROJECTED WEEKLY COST | ACTUAL WEEKLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST
| 1 | 2227.5 | 2237 | 2227.5 | 2237
| 2 | 2590 | 2600 | 4817.5 | 4837
| 3 | 4252.5 | 4003 | 9070 | 8840
| 4 | 39887.5 | 42007 | 48957.5 | 50847
| 5 | 1264128.5 | 1368594 | 1313086 | 1419441
| 6 | 769954 | 658955.67 | 2083040 | 2078396.67
| 7 | 0 | 300 | 2083040 | 2078696.67
| 8 | 0 | 1066.8 | 2083040 | 2079763.47
| 9 | 30652.5 | 32093 | 2113692.5 | 2111856.47
| 10 | 10042.5 | 10041 | 2123735 | 2121897.47

## Manual Calculations
Calculating Earned Value
WEEK | PROJECTED WEEKLY COST | ACTUAL WEEKLY COST | PROJECTED CUMULATIVE COST | ACTUAL CUMULATIVE COST (ACWP) | % Complete | BCWP | COST VARIANCE (BCWP - ACWP) | SCHEDULE VARIANCE (BCWP - BCWS) | BCWS
1 | 2227.5 | 2237 | 2227.5 | 2237 | 10%
2 | 2590 | 2600 | 4817.5 | 4837 | 15%
3 | 4252.5 | 4003 | 9070 | 8840 | 17%
4 | 39887.5 | 42007 | 48957.5 | 50847 | 20%
5 | 1264128.5 | 1368594 | 1313086 | 1419441 | 60%
6 | 769954 | 658955.67 | 2083040 | 2078396.67 | 67%
7 | 0 | 300 | 2083040 | 2078696.67 | 68%
8 | 0 | 1066.8 | 2083040 | 2079763.47 | 70%
9 | 30652.5 | 32093 | 2113692.5 | 2111856.47 | 90%
10 | 10042.5 | 10041 | 2123735 | 2121897.47 | 100%
To Calculate BCWP
1 | Add the total budget for the project, including all materials and labor to get the budgeted cost of work scheduled. For example, take a stable building project that is budgeted to use $10,000 in materials and 80 hours of labor at $20 per hour. Budgeted Cost of Work Scheduled is $10,000 + 80 x 20 = $11,600.
2 | Figure out the percent of work that has been completed. Continuing the example, 50 hours has been spent on the project but due to problems, only about 20 percent of the stable has actually been built.
3 | Multiply the budgeted cost of work scheduled by the percent of work that has been completed to get the BCWP. Finishing the example, $11,600 x 0.20 = $2,320.