Scope Statement

Date: October 8, 20xx

Project Name: 3M Salesperson Reward Trip

Project Sponsors: 3M

Original Project Managers: Sammy Holquist, Anna Kaiper, and Meg Sisk

Background & Problem Statement

In the past fiscal year, sales numbers have not been reaching the current goal. To raise performance in order to meet and try to exceed the goal, 3M will be providing the funds to plan a reward trip to the top 200 salespeople in Minnesota. Research has shown that reward trips make employees work harder after they come back from them. By rewarding salespeople with this trip, 3M hopes to increase the motivation of the team in order to continue reaching their goals.

Vision

??

Mission

??

Project Goals

- Improve salespeople's morale.

- Provide a rewarding and relaxing trip for the 3M salespeople who won the contest.

- To ensure everyone comes back to Minneapolis safely.

Project Objectives

- Recognize the names of the Top 200 3M Salespeople in Minnesota on June 30, 2017 (end of the second quarter) by rewarding them with this trip.

- Ensure that the 3M Salesperson Reward Trip is organized and ready to occur by August 30, 2017, one month prior to start date.

- Have the 100 3M Trip Employees fill out surveys on October 8, 2017 before the flight to MSP

- Receive an average rating of at least 7 out of 10 on the survey given to the 3M Trip Employees at the end of the trip October 8, 2017.

Project Scope

The project will include:

- General

  - Book travel reservations

  - Purchase airline tickets for 3M trip employees, and Project ManagersProviding lodging for all people attending the trip

- Make & execute all plans for 2 days in Chicago, including transportation, food, entertainment, and lodging.

- Make & execute all plans for 1 day in St. Louis, including transportation, food, entertainment, and lodging.

- Make & execute all plans for 1 day in Nashville, including transportation, food, entertainment, and lodging.

- Make & execute all plans for 1 day in Atlanta, including transportation, food, entertainment, and lodging.

- Make & execute all plans for 1 day in New Orleans, including transportation, food, entertainment, and lodging.

- Make & execute all plans for 3 days in Orlando, including transportation, food, entertainment, and lodging.

The project will not include:

- General

  - Transportation to 3M prior to the trip

  - Lodging for bus drivers after reaching Orlando

  - Payment or compensation of any kind to repair or replace buses

  - Event tickets, coupons, or Meal Money for the bus drivers at any point throughout the trip

  - Transportation, lodging, event tickets, coupons, Meal Money and/or any product or service of any kind for any persons not before-mentioned and not involved in the trip

  - Extra slots for people exceeding 3M Top 100 sales employees.

  - Any medical assistance not provided by the paramedics.

  - Any accommodation of flights or transportation outside of what is provided by the airline or bus company.

- Chicago

  - Information on restaurants.

  - Any event tickets, coupons, or food not before-mentioned.

- St. Louis

  - Any event tickets, coupons, or food not before-mentioned.

- Nashville

  - Transportation around downtown Nashville

  - Providing money for room service

- Atlanta

  - Transportation around the Georgia Aquarium for lunch on 10/3/16

- New Orleans

  - Information outside of pamphlets provided by hotel

  - Information on restaurants for lunch.

  - Transportation to downtown.

- Orlando

  - Transportation from Disney’s All-Star Movies Resort to any of Disney World’s theme parks (shuttles provided by Disney)

Performance Levels:

At the end of the trip, we will be handing out slips of paper to attendees that has a website url on it. The URL will be linked to a website called SurveyMonkey. There will be a survey on this website that is in regards to the bus trip we took the 100 3M employees on. The results of the survey will show how enjoyable and satisfied they were with different aspects of the trip. Every question on the survey will fall on a scale of 1 to 10, 1 being terrible and 10 being excellent. We will take the averages of all surveys over the whole trip, and that will reflect on what we need to focus on for any future projects similar to this. Our aim is to receive an average score of 7 or higher for the whole trip.